## NuP2P API v1.0
Category | Task | Day Start | Day End | Total Days Required | Comments
Login
| Login Username And Password | 1 | 5 | 5
| Forgot password -- Send to Email | 1 | 5 | 5
| Set New Password | 1 | 5 | 5
Sign Up
| Sign up message | 1 | 5 | 5
| send profile photo | 1 | 5 | 5
Loan Marketplace
| Download loan data | 6 | 10 | 5
| download photos for loans | 6 | 10 | 5
Click Invest
Fail states for investment?
Loan Marketplace - Search
| Send search request | 11 | 13 | 3
| Invest in Loan | 11 | 13 | 3
My Profile
| Withdraw Money | ??? | ??? | ???
| Update Bank Details | ??? | ??? | ??? | Is update bank details, a separate message from Withdraw money? They are both in the same sequence of operations under withdraw
| Update Address | 14 | 16 | 3
| Change Password | 14 | 16 | 3
Add Credit
| Add Credit | ??? | ??? | ??? | API Integration? We don’t know the APIs involved
Inbox
| Send message | 17 | 20 | 4 | What system will we use? The system used will cause the number of days required to vary.
| receive messages | 17 | 20 | 4 | https://conversejs.org/
| resend failed messages | 17 | 20 | 4 | http://emailjs.org/
https://github.com/katzer/cordova-plugin-email-composer
Loan Portfolio |  |  |  | 5 | Tasks still unknown
???
???
???
Dashboard Screen (Home) |  |  |  | 3
- Latest News > Link to full page of Information, HTML document based. Download from server
- Advertisement & Write-ups

## NuP2P Screens v1.2 (20160726)
Category | Task | Day Start | Day End | Total Days Required | Comments
Dashboard Screen (Home) |  |  |  | 2
| - Latest News > Link to full page of Information, HTML document based. Download from server |  |  |  | Api needed?
- Advertisement & Write-ups
Menu - My Loans Portfolio |  | ?? | ?? | 5 | Based on our previous discussion with Kelip on 22 July 2016, this is a very rough estimate of the time needed to finish the screens
- Summary of Investment
- Current Credit
| Other Tasks | ?? | ?? | ???
Menu - Settings |  | ?? | ?? | ???
| Define Settings | ?? | ?? | ??? | I need clearer details on how many settings there are, in order to better estimate the time needed for this module.
Database Storage |  | ?? | ?? | 4 | Storing local data for the app. Using SQL Databases
User Profile
Loans Portfolio
Contact Us & FAQ Screen |  | ?? | ?? | 2 | Information screens for USER
- Contact Us info
- FAQ
Inbox |  | ?? | ?? | 5
View Received Messages
View Sent Messages
Portfolio Products
| Specification to be defined | ?? | ?? | ??? | This area is still undefined, so I cannot estimate how much time is needed.
Graphs, Bar Charts
Add Credit |  | ?? | ??
Payment Gateway
Withdraw |  | ?? | ??
Payment Gateway
Optimization
| Stability Test - IOS | ?? | ?? | 2 | Ensure that Platforms run the same way and look as similar as possible.
| Stability Test - ANDROID | ?? | ?? | 2
| App Size Reduction | ?? | ?? | 2 | App size too large. Try to reduce as much as possible.
| Code Obfuscation/Encryption | ?? | ?? | 3 | All code is written in html, css, js. It needs to be obfuscated before published for release online. We may need to BUY 3rd party professional tool to hide the codes. This requires research.

## NuP2P (Revised 20160721)
NuP2P App (Android, iOS & Web Platform) Targeted OS Version: API Level: App Size:
Developer: Brian | Target Start Date | Target End Date | DURATION | COMMENTS
Requirement Study (2 weeks)
UI Design
Feature Design
Final Prototype for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
Unknow User (Without Login)
1) Splash Screen | DONE | DONE | DONE
- App Launch -> Logo (Default) Images | DONE | DONE | DONE
2) Dashboard Screen (Home)
- Latest News > Link to full page of Information, HTML document based. Download from server | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Advertisement & Write-ups | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Navigation Products Summary in listview | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Search Box (filter by Rating, Loan Amount & Tenure) | DONE | DONE | DONE | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> P2P Product Catalogue in Brief | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> Click to view full details (required user to signup to view full product details) | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> Click to view full details (required user to signup to view full product details) | ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| ?? | ?? | ?? | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
3) Sign Up
- Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) | DONE | DONE | DONE
| DONE | DONE | DONE
> Email Account Verification | DONE | DONE | DONE
Registered User
1) Splash Screen | DONE | DONE | DONE
- App Launch -> Logo (Default) Images | DONE | DONE | DONE
2) Login Screen
- Info on P2P Lending Application | DONE | DONE | DONE
> Videos (Download) | DONE | DONE | DONE | Dependent on specification
- Login | DONE | DONE | DONE
> Email & Password & Verify/Link to Mobile | DONE | DONE | DONE
- Forgot Password? | DONE | DONE | DONE
> Reset Password | DONE | DONE | DONE
- Sign Up (New User) | DONE | DONE | DONE
> Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) | DONE | DONE | DONE
| DONE | DONE | DONE
> Email Account Verification | DONE | DONE | DONE | Henny for backend comms
3) Dashboard Screen (Home)
- Header Panel | DONE | DONE | DONE
> Menu | DONE | DONE | DONE
- Latest News > Link to full page of Information, HTML document based. Download from server | ?? | ?? | ??
| ?? | ?? | ??
- Advertisement & Write-ups | ?? | ?? | ??
- Navigation Products Summary in listview | ?? | ?? | ??
- Search Box (filter by Rating, Loan Amount & Tenure) | DONE | DONE | DONE | API Discuss with Henny
> P2P Product Catalogue | DONE | DONE | DONE
> Click to view full details | DONE | DONE | DONE
> Click to Invest (if no credit) | DONE | DONE | DONE
> Add Credit | DONE | DONE | DONE
> Select Payment Mode > Payment Gateway | ?? | ?? | ??
> Click to Invest (with credit) | DONE | DONE | DONE
> Confirmation of Investment add into Portfolio | ?? | ?? | ??
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | ?? | ?? | ??
| ?? | ?? | ??
> Click to view full details | ?? | ?? | ??
> Add Credit | DONE | DONE | DONE
> Select Payment Mode > Payment Gateway | DONE | DONE | DONE
> Click to Invest (with credit) | DONE | DONE | DONE
> Confirmation of Investment add into Portfolio | DONE | DONE | DONE
4) Sliding Drawer Menu |  |  | 1
- Home (Dashboard) | DONE | DONE | DONE
- Inbox | DONE | DONE | DONE
> Message & Feedback | DONE | DONE | DONE
- Loans Marketplace | DONE | DONE | DONE
> Catalogue of Loan Products | DONE | DONE | DONE
> Loan Products Detailed Info & Invest | DONE | DONE | DONE
- My Loans Portfolio | ?? | ?? | ??
- My Profile | DONE | DONE | DONE
> Name, Email, Mobile No & Date of Birth | DONE | DONE | DONE
> Change Password | DONE | DONE | DONE
- Contact Us / FAQ | DONE | DONE | DONE
- Settings | ?? | ?? | ??
- Logout (Exit) | DONE | DONE | DONE
5) Inbox Screen
- Message & Feedback | ?? | ?? | ??
6) Loan Marketplace Screen | DONE | DONE | DONE
- Catalogue of Loan Products | DONE | DONE | DONE
> Loan Products Detailed Info & Invest | DONE | DONE | DONE
7) My Loans Portfolio Screen
- Summary of Investment | ?? | ?? | ??
- Current Credit | ?? | ?? | ??
8) My Profile Screen
- Name, Email, Mobile No & Date of Birth | 2016-07-21 | 2016-07-24 | 4
> Change Password | 2016-07-21 | 2016-07-24 | 4
9) Contact Us & FAQ Screen
- Contact Us info | ?? | ?? | ??
- FAQ | ?? | ?? | ??
10) Setting Screen
- About App Setting? | ?? | ?? | ?? | To Be Discussed
(11) - Platform Testing
IOS | ?? | ?? | ?? | Ensure that Platforms run the same way and look as similar as possible.
Android | ?? | ??

## NuP2P
NuP2P App (Android, iOS & Web Platform) Targeted OS Version: API Level: App Size:
Developer: Brian | Target Start Date | Target End Date | DURATION | COMMENTS
Requirement Study (2 weeks)
UI Design
Feature Design
Final Prototype for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
Unknow User (Without Login)
1) Splash Screen | DONE | DONE | DONE
- App Launch -> Logo (Default) Images | DONE | DONE | DONE
2) Dashboard Screen (Home)
- Latest News > Link to full page of Information, HTML document based. Download from server | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Advertisement & Write-ups | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Navigation Products Summary in listview | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Search Box (filter by Rating, Loan Amount & Tenure) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> P2P Product Catalogue in Brief | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> Click to view full details (required user to signup to view full product details) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> Click to view full details (required user to signup to view full product details) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
3) Sign Up | 2016-06-27 | 2016-07-01 | 5
- Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) | 2016-06-27 | 2016-07-01 | 5
| 2016-06-27 | 2016-07-01 | 5
> Email Account Verification | 2016-06-27 | 2016-07-01 | 5
Registered User
1) Splash Screen | DONE | DONE
- App Launch -> Logo (Default) Images | DONE | DONE
2) Login Screen |  |  | 1
- Info on P2P Lending Application |  |  | 1
> Videos (Download) | ? | ? |  | Dependent on specification
- Login | 2016-06-27 | 2016-07-01 | 5
> Email & Password & Verify/Link to Mobile | 2016-06-27 | 2016-07-01 | 5
- Forgot Password? | 2016-06-27 | 2016-07-01 | 5
> Reset Password | 2016-06-27 | 2016-07-01 | 5
- Sign Up (New User) | 2016-06-27 | 2016-07-01 | 5
> Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) | 2016-06-27 | 2016-07-01 | 5
| 2016-06-27 | 2016-07-01 | 5
> Email Account Verification | ? | ? |  | Henny for backend comms
3) Dashboard Screen (Home) |  |  | 1
- Header Panel | 2016-07-11 | 2016-07-15 | 5
> Menu | 2016-07-11 | 2016-07-15 | 5
- Latest News > Link to full page of Information, HTML document based. Download from server | 2016-07-11 | 2016-07-15 | 5
| 2016-07-11 | 2016-07-15 | 5
- Advertisement & Write-ups | 2016-07-11 | 2016-07-15 | 5
- Navigation Products Summary in listview | 2016-07-11 | 2016-07-15 | 5
- Search Box (filter by Rating, Loan Amount & Tenure) | 2016-07-11 | 2016-07-15 | 5 | API Discuss with Henny
> P2P Product Catalogue | 2016-07-11 | 2016-07-15 | 5
> Click to view full details | 2016-07-11 | 2016-07-15 | 5
> Click to Invest (if no credit) | 2016-07-11 | 2016-07-15 | 5
> Add Credit | 2016-07-11 | 2016-07-15 | 5
> Select Payment Mode > Payment Gateway | 2016-07-11 | 2016-07-15 | 5
> Click to Invest (with credit) | 2016-07-11 | 2016-07-15 | 5
> Confirmation of Investment add into Portfolio | 2016-07-11 | 2016-07-15 | 5
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | 2016-07-11 | 2016-07-15 | 5
| 2016-07-11 | 2016-07-15 | 5
> Click to view full details | 2016-07-11 | 2016-07-15 | 5
| 2016-07-11 | 2016-07-15 | 5
> Add Credit | 2016-07-11 | 2016-07-15 | 5
> Select Payment Mode > Payment Gateway | 2016-07-11 | 2016-07-15 | 5
> Click to Invest (with credit) | 2016-07-11 | 2016-07-15 | 5
> Confirmation of Investment add into Portfolio | 2016-07-11 | 2016-07-15 | 5
4) Sliding Drawer Menu |  |  | 1
- Home (Dashboard) | 2016-07-18 | 2016-07-22 | 5
- Inbox | 2016-07-18 | 2016-07-22 | 5
> Message & Feedback | 2016-07-18 | 2016-07-22 | 5
- Loans Marketplace | 2016-07-18 | 2016-07-22 | 5
> Catalogue of Loan Products | 2016-07-18 | 2016-07-22 | 5
> Loan Products Detailed Info & Invest | 2016-07-18 | 2016-07-22 | 5
- My Loans Portfolio | 2016-07-18 | 2016-07-22 | 5
- My Profile | 2016-07-18 | 2016-07-22 | 5
> Name, Email, Mobile No & Date of Birth | 2016-07-18 | 2016-07-22 | 5
> Change Password | 2016-07-18 | 2016-07-22 | 5
- Contact Us / FAQ | 2016-07-18 | 2016-07-22 | 5
- Settings | 2016-07-18 | 2016-07-22 | 5
- Logout (Exit) | 2016-07-18 | 2016-07-22 | 5
5) Inbox Screen
- Message & Feedback | 2016-07-25 | 2016-07-29 | 5
6) Loan Marketplace Screen
- Catalogue of Loan Products | 2016-07-25 | 2016-07-29 | 5
> Loan Products Detailed Info & Invest | 2016-07-25 | 2016-07-29 | 5
7) My Loans Portfolio Screen
- Summary of Investment | 2016-07-25 | 2016-07-29 | 5
- Current Credit | 2016-07-25 | 2016-07-29 | 5
8) My Profile Screen
- Name, Email, Mobile No & Date of Birth | 2016-07-25 | 2016-07-29 | 5
> Change Password | 2016-07-25 | 2016-07-29 | 5
9) Contact Us & FAQ Screen
- Contact Us info | 2016-07-25 | 2016-07-29 | 5
- FAQ | 2016-07-25 | 2016-07-29 | 5
10) Setting Screen
- About App Setting? | 2016-07-25 | 2016-07-29 | 5 | To Be Discussed

## NuAcacia Features
LIST OF APPLICATION FEATURES
NuAcacia Operations System (Central Server)
NuP2P App (Android, iOS & Web Platform) Targeted OS Version: API Level: App Size: |  | NuKash App (Web & Android Platform) Targeted OS Version: API Level: App Size: | NuCollect App (Android Platform) Targeted OS Version: API Level: App Size: | Admin Portal (Web Platform) | Payment Gateway (Web Platform) | Credit Scoring Engine
Developer: Brian |  | Developer: Jie Yong | Developer: Duncan | Developer: Henny & Kean Fook | Developer: To Be Determined | Developer: Henny
Requirement Study (2 weeks)
UI Design
Feature Design
Final Prototype for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
Unknow User (Without Login) | 1st Build (27 Jun to 30 Jun)
1) Splash Screen | 1 Day | 1) Splash Screen | 1) Splash Screen | 1) Login Screen | Payment methods: credit cards / bank transfers | Criteria Enhancement
- App Launch -> Logo (Default) Images |  | - App Launch -> Logo (Default) Images | - App Launch -> Logo (Default) Images | 2) NuKash Mobile API
2) Dashboard Screen (Home) | 2 Days | 2) Login Screen | 2) Login Screen | 3) Borrowers Management (Admin Portal)
- Latest News > Link to full page of Information, HTML document based. Download from server |  | - Info on Micro Lending | - Login | - Rate the Loan Application (Back Engine)
|  | > Videos (Download) | > Email & Password | - Review Loan Application
- Advertisement & Write-ups |  | - Login | - Forgot Password? | > Application Status
- Navigation Products Summary in listview |  | > Email & Password & Verify & Link to Mobile | > Reset Password | > Approve
- Search Box (filter by Rating, Loan Amount & Tenure) |  | - Forgot Password? | - Activate Login | > Reject
> P2P Product Catalogue in Brief |  | > Reset Password | > Activation Code | > Adjust
> Click to view full details (required user to signup to view full product details) |  | - Sign Up (New User) | > Email, Password & Re-type Password | > Tenure
|  | > Name & Email | > Login Again | > Interests
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) |  | 3) Dashboard Screen (Home) | 2) Dashboard Screen (Home) | > Repayment Schedule
|  | - Apply Loan | - Header Panel | - Loan Disbursement
> Click to view full details (required user to signup to view full product details) |  | > Loan & Income | > Menu | > Agreement
|  | > Personal & Employment | - Home (Dashboard) | > Date
3) Sign Up | 1 Day | 4) Sliding Drawer Menu | - Job Locator (by Map & List View, Job Details) | > Borrower Bank Account
- Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) |  | - Home (Dashboard) | - My Jobs (Job List) | - Continue Loan
|  | - Inbox | - My ID | - Track Borrow Payment
> Email Account Verification |  | > Message & Feedback | - My Account/Setting | > Date
|  | - Loan Status | - Logout | > Amount
Registered User |  | > Loan Disbursement Documentation | - Job List (Today, 2-Day & 3-Day) | - Restructure Loan
1) Splash Screen |  | - My Profile | - Job Locator (Locate Job) | 4) Borrowers Management (Back Engine)
- App Launch -> Logo (Default) Images |  | > Name, Email & Change Password | - Performance | - Push Outstanding Loan to Collector App
2) Login Screen |  | - Contact Us / FAQ | > Total Jobs Done in Last 1 Week | - Receive Status from Collector App (API)
- Info on P2P Lending Application |  | - Settings | > Total Jobs Done in Last 1 Month | 5) Reporting (Performance Management)
> Videos (Download) |  | - Logout (Exit) | > Total Jobs (in Qty) = RMxxx | - Daily¦Weekly¦Monthly (Disbursement)
- Login |  |  | > Total Earned RMxxx | - Daily¦Weekly¦Monthly (Repayment)
> Email & Password & Verify/Link to Mobile |  |  | > Total Emergency Job Pickups (point count) | 6) User Management (Admin Portal)
- Forgot Password? |  |  | > Total Job Cancel Due to Emergency (point count) | Country - Region Level
> Reset Password |  |  | 3) Job List Screen (My Job) | User Group
- Sign Up (New User) |  |  | - Total Pending Jobs | Borrowers
> Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) |  |  | - Today's Jobs Details (Max 3 Jobs) | P2P Users
|  |  | - 2-Day Jobs Details (Max 3 Jobs) | Collector
> Email Account Verification |  |  | - 3-Day's Jobs Details (Max 3 Jobs) | Operations Support
3) Dashboard Screen (Home) |  |  | - Cancel Job due to emergency | Loan Officer (View¦Verify)
- Header Panel |  |  | 4) Job Locator Screen | Credit Operation (Credit Review¦Approve/Reject)
> Menu |  |  | - Navigation Map View | Credit Portfolio Management (Review¦Approve Disbursement)
- Latest News > Link to full page of Information, HTML document based. Download from server |  |  | - Radius Slider | Finance (View¦Update)
|  |  | > 3 Locator icons | User Account
- Advertisement & Write-ups |  |  | - Red = 1-Day Job (emergency_ | User Roles
- Navigation Products Summary in listview |  |  | - Orange = 2-Day Job | 7) Catalogue/Portfolio Product (Admin Portal)
- Search Box (filter by Rating, Loan Amount & Tenure) |  |  | - Green = 3-Day Job | - Setup Catalogue Product
> P2P Product Catalogue |  |  | - List View | > Product Name
> Click to view full details |  |  | - Job Details > Job Start (to be confirmed) | > Description
> Click to Invest (if no credit) |  |  | 5) Job Details Screen (to be confirmed) | > Effective Period
> Add Credit |  |  | - Job Start | > % Return Per Annum (RPA)
> Select Payment Mode > Payment Gateway |  |  | > Video & Voice Recording | > Product Period (in days)
> Click to Invest (with credit) |  |  | > Take Photo | 8) Publish Approved Borrowers
> Confirmation of Investment add into Portfolio |  |  | > Upload Record | 9) Get Products/Borrowers List (API)
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) |  |  | > Job Completed & Submit | 10) Investor Management (APP)
|  |  | 6) My ID Screen | - Register as Investor
> Click to view full details |  |  | - Profile Picture, Name, ID No & QR | - Top-up e-Wallet
> Click to Invest (if no credit) |  |  | 7) My Profile/Setting Screen | - Purchase Product
> Add Credit |  |  | > Name, Email & Mobile No | - Withdraw from e-Wallet
> Select Payment Mode > Payment Gateway |  |  | > Change Password | - View Transactions
> Click to Invest (with credit) |  |  |  | - View Product/Catalogue
> Confirmation of Investment add into Portfolio |  |  |  | 11) Investor Management (Admin Portal)
4) Sliding Drawer Menu |  |  |  | - Approve Registration/Top-up/Withdrawal
- Home (Dashboard) |  |  |  | - Process Purchase of Product
- Inbox |  |  |  | - View Transactions
> Message & Feedback |  |  |  | - Edit Investor Profile (Level?)
- Loans Marketplace
> Catalogue of Loan Products
> Loan Products Detailed Info & Invest
- My Loans Portfolio
- My Profile
> Name, Email, Mobile No & Date of Birth
> Change Password
- Contact Us / FAQ
- Settings
- Logout (Exit)
5) Inbox Screen
- Message & Feedback
6) Loan Marketplace Screen
- Catalogue of Loan Products
> Loan Products Detailed Info & Invest
7) My Loans Portfolio Screen
- Summary of Investment
- Current Credit
8) My Profile Screen
- Name, Email, Mobile No & Date of Birth
> Change Password
9) Contact Us & FAQ Screen
- Contact Us info
- FAQ
10) Setting Screen
- About App Setting?

## NuKash Features 1.0
LIST OF APPLICATION FEATURES | NuAcacia Operations System (Central Server)
| NuP2P App (Android, iOS & Web Platform) |  |  |  | NuKash App (Web & Android Platform) | NuCollect App (Android Platform) | OpsApp (Window) | Credit Scoring Engine
| Developer: Brian | Target Start Date | Target End Date | DURATION | Developer: Henny | Developer: Duncan | Developer: To be Determined (Nominated by Kelip) | Developer: Henny
Requirement Study (2 weeks)
UI Design
Feature Design
Final Proto for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
1) Flash Screen | ü | Done | Done | Done
- App Launch -> Logo (Default) Images | ü | Done | Done | Done
2) Login Screen | ü |  |  |  |  | 1) Login Screen
- Info on P2P Lending Application | ü | 2016-06-27 | 2016-07-01
> Videos (Download) | ü | 2016-06-27 | 2016-07-01
- Login | ü | 2016-06-27 | 2016-07-01 |  |  | - Login
> Email & Password & Verify & Link to Mobile | ü | 2016-06-27 | 2016-07-01 |  |  | > Email & Password & Verify & Link to Mobile
- Forgot Password? | ü | 2016-06-27 | 2016-07-01 |  |  | - Forgot Password?
> Reset Password | ü | 2016-06-27 | 2016-07-01 |  |  | > Reset Password
- Sign Up (New User) | ü | 2016-06-27 | 2016-07-01
> Name & Email | ü | 2016-06-27 | 2016-07-01
3) Dashboard Screen (Home) | ü |  |  |  |  | 2) Dashboard Screen (Home)
- Header Panel | ü |  |  |  |  | - Header Panel
> Menu | ü |  |  |  |  | > Menu
> Search Box (filter by Rating, Loan Amount & Tenure) | ü |  |  |  |  | > Search Box (Job Pick up filter by Location & Job Urgency)
> Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | ü |  |  |  |  | > Navigation Map (view Jobs in Area within assigned radius territory)
| ü |  |  |  |  | > List View Jobs
- Advertisement Banner | ü |  |  |  |  | - Job Pickups Listing
> Latest News Link to full page of information. HTML document based. Download from server. | ü |  |  |  |  | > Pickup & Confirmation
| ü |  |  |  |  | > Pending Jobs (by Days or Location to Complete)
- Navigation P2P Summary info in listview | ü |  |  |  |  | > Emergency Cancellation
> Scroll Down for more Info | ü |  |  |  |  | > Pickup Emergency Jobs (Emergency Job Notification)
> Press on section for more details | ü |  |  |  |  | > Video & Voice Recording, Take Picture & Upload Records
4) Sliding Drawer Menu | ü |  |  |  |  | 3) Sliding Drawer Menu
- Sliding Menu with Buttons |  | Done | Done | Done
- Home (Dashboard) | ü |  |  |  |  | - Home (Dashboard)
- Inbox | ü |  |  |  |  | - Inbox
> Message & Feedback | ü |  |  |  |  | > Message & Feedback
- Loans Marketplace | ü |  |  |  |  | - Job Pickups
> Catalogue of Loan Products | ü
> Loan Products Detailed Info | ü
- My Loans Portfolio | ü
- My Profile | ü |  |  |  |  | - My Profile
> Name, Email & Change Password | ü |  |  |  |  | > Name, Email & Change Password
- Contact Us / FAQ | ü
- Settings | ü
- Logout (Exit) | ü |  |  |  |  | - Logout (Exit)