## NuP2P
NuP2P App (Android, iOS & Web Platform) Targeted OS Version: API Level: App Size:
Developer: Brian | Target Start Date | Target End Date | DURATION | COMMENTS
Requirement Study (2 weeks)
UI Design
Feature Design
Final Prototype for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
Unknow User (Without Login)
1) Splash Screen | DONE | DONE | DONE
- App Launch -> Logo (Default) Images | DONE | DONE | DONE
2) Dashboard Screen (Home)
- Latest News > Link to full page of Information, HTML document based. Download from server | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Advertisement & Write-ups | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Navigation Products Summary in listview | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
- Search Box (filter by Rating, Loan Amount & Tenure) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> P2P Product Catalogue in Brief | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> Click to view full details (required user to signup to view full product details) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
> Click to view full details (required user to signup to view full product details) | 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
| 2016-07-04 | 2016-07-08 | 5 | Henny for backend comms. Tentatively set to 2nd week assuming his side can be ready by then.
3) Sign Up | 2016-06-27 | 2016-07-01 | 5
- Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) | 2016-06-27 | 2016-07-01 | 5
| 2016-06-27 | 2016-07-01 | 5
> Email Account Verification | 2016-06-27 | 2016-07-01 | 5
Registered User
1) Splash Screen | DONE | DONE
- App Launch -> Logo (Default) Images | DONE | DONE
2) Login Screen |  |  | 1
- Info on P2P Lending Application |  |  | 1
> Videos (Download) | ? | ? |  | Dependent on specification
- Login | 2016-06-27 | 2016-07-01 | 5
> Email & Password & Verify/Link to Mobile | 2016-06-27 | 2016-07-01 | 5
- Forgot Password? | 2016-06-27 | 2016-07-01 | 5
> Reset Password | 2016-06-27 | 2016-07-01 | 5
- Sign Up (New User) | 2016-06-27 | 2016-07-01 | 5
> Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) | 2016-06-27 | 2016-07-01 | 5
| 2016-06-27 | 2016-07-01 | 5
> Email Account Verification | ? | ? |  | Henny for backend comms
3) Dashboard Screen (Home) |  |  | 1
- Header Panel | 2016-07-11 | 2016-07-15 | 5
> Menu | 2016-07-11 | 2016-07-15 | 5
- Latest News > Link to full page of Information, HTML document based. Download from server | 2016-07-11 | 2016-07-15 | 5
| 2016-07-11 | 2016-07-15 | 5
- Advertisement & Write-ups | 2016-07-11 | 2016-07-15 | 5
- Navigation Products Summary in listview | 2016-07-11 | 2016-07-15 | 5
- Search Box (filter by Rating, Loan Amount & Tenure) | 2016-07-11 | 2016-07-15 | 5 | API Discuss with Henny
> P2P Product Catalogue | 2016-07-11 | 2016-07-15 | 5
> Click to view full details | 2016-07-11 | 2016-07-15 | 5
> Click to Invest (if no credit) | 2016-07-11 | 2016-07-15 | 5
> Add Credit | 2016-07-11 | 2016-07-15 | 5
> Select Payment Mode > Payment Gateway | 2016-07-11 | 2016-07-15 | 5
> Click to Invest (with credit) | 2016-07-11 | 2016-07-15 | 5
> Confirmation of Investment add into Portfolio | 2016-07-11 | 2016-07-15 | 5
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | 2016-07-11 | 2016-07-15 | 5
| 2016-07-11 | 2016-07-15 | 5
> Click to view full details | 2016-07-11 | 2016-07-15 | 5
| 2016-07-11 | 2016-07-15 | 5
> Add Credit | 2016-07-11 | 2016-07-15 | 5
> Select Payment Mode > Payment Gateway | 2016-07-11 | 2016-07-15 | 5
> Click to Invest (with credit) | 2016-07-11 | 2016-07-15 | 5
> Confirmation of Investment add into Portfolio | 2016-07-11 | 2016-07-15 | 5
4) Sliding Drawer Menu |  |  | 1
- Home (Dashboard) | 2016-07-18 | 2016-07-22 | 5
- Inbox | 2016-07-18 | 2016-07-22 | 5
> Message & Feedback | 2016-07-18 | 2016-07-22 | 5
- Loans Marketplace | 2016-07-18 | 2016-07-22 | 5
> Catalogue of Loan Products | 2016-07-18 | 2016-07-22 | 5
> Loan Products Detailed Info & Invest | 2016-07-18 | 2016-07-22 | 5
- My Loans Portfolio | 2016-07-18 | 2016-07-22 | 5
- My Profile | 2016-07-18 | 2016-07-22 | 5
> Name, Email, Mobile No & Date of Birth | 2016-07-18 | 2016-07-22 | 5
> Change Password | 2016-07-18 | 2016-07-22 | 5
- Contact Us / FAQ | 2016-07-18 | 2016-07-22 | 5
- Settings | 2016-07-18 | 2016-07-22 | 5
- Logout (Exit) | 2016-07-18 | 2016-07-22 | 5
5) Inbox Screen
- Message & Feedback | 2016-07-25 | 2016-07-29 | 5
6) Loan Marketplace Screen
- Catalogue of Loan Products | 2016-07-25 | 2016-07-29 | 5
> Loan Products Detailed Info & Invest | 2016-07-25 | 2016-07-29 | 5
7) My Loans Portfolio Screen
- Summary of Investment | 2016-07-25 | 2016-07-29 | 5
- Current Credit | 2016-07-25 | 2016-07-29 | 5
8) My Profile Screen
- Name, Email, Mobile No & Date of Birth | 2016-07-25 | 2016-07-29 | 5
> Change Password | 2016-07-25 | 2016-07-29 | 5
9) Contact Us & FAQ Screen
- Contact Us info | 2016-07-25 | 2016-07-29 | 5
- FAQ | 2016-07-25 | 2016-07-29 | 5
10) Setting Screen
- About App Setting? | 2016-07-25 | 2016-07-29 | 5 | To Be Discussed

## NuAcacia Features
LIST OF APPLICATION FEATURES
NuAcacia Operations System (Central Server)
NuP2P App (Android, iOS & Web Platform) Targeted OS Version: API Level: App Size: |  | NuKash App (Web & Android Platform) Targeted OS Version: API Level: App Size: | NuCollect App (Android Platform) Targeted OS Version: API Level: App Size: | Admin Portal (Web Platform) | Payment Gateway (Web Platform) | Credit Scoring Engine
Developer: Brian |  | Developer: Jie Yong | Developer: Duncan | Developer: Henny & Kean Fook | Developer: To Be Determined | Developer: Henny
Requirement Study (2 weeks)
UI Design
Feature Design
Final Prototype for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
Unknow User (Without Login) | 1st Build (27 Jun to 30 Jun)
1) Splash Screen | 1 Day | 1) Splash Screen | 1) Splash Screen | 1) Login Screen | Payment methods: credit cards / bank transfers | Criteria Enhancement
- App Launch -> Logo (Default) Images |  | - App Launch -> Logo (Default) Images | - App Launch -> Logo (Default) Images | 2) NuKash Mobile API
2) Dashboard Screen (Home) | 2 Days | 2) Login Screen | 2) Login Screen | 3) Borrowers Management (Admin Portal)
- Latest News > Link to full page of Information, HTML document based. Download from server |  | - Info on Micro Lending | - Login | - Rate the Loan Application (Back Engine)
|  | > Videos (Download) | > Email & Password | - Review Loan Application
- Advertisement & Write-ups |  | - Login | - Forgot Password? | > Application Status
- Navigation Products Summary in listview |  | > Email & Password & Verify & Link to Mobile | > Reset Password | > Approve
- Search Box (filter by Rating, Loan Amount & Tenure) |  | - Forgot Password? | - Activate Login | > Reject
> P2P Product Catalogue in Brief |  | > Reset Password | > Activation Code | > Adjust
> Click to view full details (required user to signup to view full product details) |  | - Sign Up (New User) | > Email, Password & Re-type Password | > Tenure
|  | > Name & Email | > Login Again | > Interests
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) |  | 3) Dashboard Screen (Home) | 2) Dashboard Screen (Home) | > Repayment Schedule
|  | - Apply Loan | - Header Panel | - Loan Disbursement
> Click to view full details (required user to signup to view full product details) |  | > Loan & Income | > Menu | > Agreement
|  | > Personal & Employment | - Home (Dashboard) | > Date
3) Sign Up | 1 Day | 4) Sliding Drawer Menu | - Job Locator (by Map & List View, Job Details) | > Borrower Bank Account
- Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) |  | - Home (Dashboard) | - My Jobs (Job List) | - Continue Loan
|  | - Inbox | - My ID | - Track Borrow Payment
> Email Account Verification |  | > Message & Feedback | - My Account/Setting | > Date
|  | - Loan Status | - Logout | > Amount
Registered User |  | > Loan Disbursement Documentation | - Job List (Today, 2-Day & 3-Day) | - Restructure Loan
1) Splash Screen |  | - My Profile | - Job Locator (Locate Job) | 4) Borrowers Management (Back Engine)
- App Launch -> Logo (Default) Images |  | > Name, Email & Change Password | - Performance | - Push Outstanding Loan to Collector App
2) Login Screen |  | - Contact Us / FAQ | > Total Jobs Done in Last 1 Week | - Receive Status from Collector App (API)
- Info on P2P Lending Application |  | - Settings | > Total Jobs Done in Last 1 Month | 5) Reporting (Performance Management)
> Videos (Download) |  | - Logout (Exit) | > Total Jobs (in Qty) = RMxxx | - Daily¦Weekly¦Monthly (Disbursement)
- Login |  |  | > Total Earned RMxxx | - Daily¦Weekly¦Monthly (Repayment)
> Email & Password & Verify/Link to Mobile |  |  | > Total Emergency Job Pickups (point count) | 6) User Management (Admin Portal)
- Forgot Password? |  |  | > Total Job Cancel Due to Emergency (point count) | Country - Region Level
> Reset Password |  |  | 3) Job List Screen (My Job) | User Group
- Sign Up (New User) |  |  | - Total Pending Jobs | Borrowers
> Create Account (Email, Password, Confirmed Password, Mobile No, Date of Birth) |  |  | - Today's Jobs Details (Max 3 Jobs) | P2P Users
|  |  | - 2-Day Jobs Details (Max 3 Jobs) | Collector
> Email Account Verification |  |  | - 3-Day's Jobs Details (Max 3 Jobs) | Operations Support
3) Dashboard Screen (Home) |  |  | - Cancel Job due to emergency | Loan Officer (View¦Verify)
- Header Panel |  |  | 4) Job Locator Screen | Credit Operation (Credit Review¦Approve/Reject)
> Menu |  |  | - Navigation Map View | Credit Portfolio Management (Review¦Approve Disbursement)
- Latest News > Link to full page of Information, HTML document based. Download from server |  |  | - Radius Slider | Finance (View¦Update)
|  |  | > 3 Locator icons | User Account
- Advertisement & Write-ups |  |  | - Red = 1-Day Job (emergency_ | User Roles
- Navigation Products Summary in listview |  |  | - Orange = 2-Day Job | 7) Catalogue/Portfolio Product (Admin Portal)
- Search Box (filter by Rating, Loan Amount & Tenure) |  |  | - Green = 3-Day Job | - Setup Catalogue Product
> P2P Product Catalogue |  |  | - List View | > Product Name
> Click to view full details |  |  | - Job Details > Job Start (to be confirmed) | > Description
> Click to Invest (if no credit) |  |  | 5) Job Details Screen (to be confirmed) | > Effective Period
> Add Credit |  |  | - Job Start | > % Return Per Annum (RPA)
> Select Payment Mode > Payment Gateway |  |  | > Video & Voice Recording | > Product Period (in days)
> Click to Invest (with credit) |  |  | > Take Photo | 8) Publish Approved Borrowers
> Confirmation of Investment add into Portfolio |  |  | > Upload Record | 9) Get Products/Borrowers List (API)
> List of Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) |  |  | > Job Completed & Submit | 10) Investor Management (APP)
|  |  | 6) My ID Screen | - Register as Investor
> Click to view full details |  |  | - Profile Picture, Name, ID No & QR | - Top-up e-Wallet
> Click to Invest (if no credit) |  |  | 7) My Profile/Setting Screen | - Purchase Product
> Add Credit |  |  | > Name, Email & Mobile No | - Withdraw from e-Wallet
> Select Payment Mode > Payment Gateway |  |  | > Change Password | - View Transactions
> Click to Invest (with credit) |  |  |  | - View Product/Catalogue
> Confirmation of Investment add into Portfolio |  |  |  | 11) Investor Management (Admin Portal)
4) Sliding Drawer Menu |  |  |  | - Approve Registration/Top-up/Withdrawal
- Home (Dashboard) |  |  |  | - Process Purchase of Product
- Inbox |  |  |  | - View Transactions
> Message & Feedback |  |  |  | - Edit Investor Profile (Level?)
- Loans Marketplace
> Catalogue of Loan Products
> Loan Products Detailed Info & Invest
- My Loans Portfolio
- My Profile
> Name, Email, Mobile No & Date of Birth
> Change Password
- Contact Us / FAQ
- Settings
- Logout (Exit)
5) Inbox Screen
- Message & Feedback
6) Loan Marketplace Screen
- Catalogue of Loan Products
> Loan Products Detailed Info & Invest
7) My Loans Portfolio Screen
- Summary of Investment
- Current Credit
8) My Profile Screen
- Name, Email, Mobile No & Date of Birth
> Change Password
9) Contact Us & FAQ Screen
- Contact Us info
- FAQ
10) Setting Screen
- About App Setting?

## NuKash Features 1.0
LIST OF APPLICATION FEATURES | NuAcacia Operations System (Central Server)
| NuP2P App (Android, iOS & Web Platform) |  |  |  | NuKash App (Web & Android Platform) | NuCollect App (Android Platform) | OpsApp (Window) | Credit Scoring Engine
| Developer: Brian | Target Start Date | Target End Date | DURATION | Developer: Henny | Developer: Duncan | Developer: To be Determined (Nominated by Kelip) | Developer: Henny
Requirement Study (2 weeks)
UI Design
Feature Design
Final Proto for Dev
Weekly Build Release Review
Internal UAT (2 Months)
Functional Soft Launch (1 Week)
Feedback & reworks ( 1 week)
Go Live (3 Months)
1) Flash Screen | ü | Done | Done | Done
- App Launch -> Logo (Default) Images | ü | Done | Done | Done
2) Login Screen | ü |  |  |  |  | 1) Login Screen
- Info on P2P Lending Application | ü | 2016-06-27 | 2016-07-01
> Videos (Download) | ü | 2016-06-27 | 2016-07-01
- Login | ü | 2016-06-27 | 2016-07-01 |  |  | - Login
> Email & Password & Verify & Link to Mobile | ü | 2016-06-27 | 2016-07-01 |  |  | > Email & Password & Verify & Link to Mobile
- Forgot Password? | ü | 2016-06-27 | 2016-07-01 |  |  | - Forgot Password?
> Reset Password | ü | 2016-06-27 | 2016-07-01 |  |  | > Reset Password
- Sign Up (New User) | ü | 2016-06-27 | 2016-07-01
> Name & Email | ü | 2016-06-27 | 2016-07-01
3) Dashboard Screen (Home) | ü |  |  |  |  | 2) Dashboard Screen (Home)
- Header Panel | ü |  |  |  |  | - Header Panel
> Menu | ü |  |  |  |  | > Menu
> Search Box (filter by Rating, Loan Amount & Tenure) | ü |  |  |  |  | > Search Box (Job Pick up filter by Location & Job Urgency)
> Catalogue of Borrowers (list of Businesses that are looking to secure loans via the Acacia platform) | ü |  |  |  |  | > Navigation Map (view Jobs in Area within assigned radius territory)
| ü |  |  |  |  | > List View Jobs
- Advertisement Banner | ü |  |  |  |  | - Job Pickups Listing
> Latest News Link to full page of information. HTML document based. Download from server. | ü |  |  |  |  | > Pickup & Confirmation
| ü |  |  |  |  | > Pending Jobs (by Days or Location to Complete)
- Navigation P2P Summary info in listview | ü |  |  |  |  | > Emergency Cancellation
> Scroll Down for more Info | ü |  |  |  |  | > Pickup Emergency Jobs (Emergency Job Notification)
> Press on section for more details | ü |  |  |  |  | > Video & Voice Recording, Take Picture & Upload Records
4) Sliding Drawer Menu | ü |  |  |  |  | 3) Sliding Drawer Menu
- Sliding Menu with Buttons |  | Done | Done | Done
- Home (Dashboard) | ü |  |  |  |  | - Home (Dashboard)
- Inbox | ü |  |  |  |  | - Inbox
> Message & Feedback | ü |  |  |  |  | > Message & Feedback
- Loans Marketplace | ü |  |  |  |  | - Job Pickups
> Catalogue of Loan Products | ü
> Loan Products Detailed Info | ü
- My Loans Portfolio | ü
- My Profile | ü |  |  |  |  | - My Profile
> Name, Email & Change Password | ü |  |  |  |  | > Name, Email & Change Password
- Contact Us / FAQ | ü
- Settings | ü
- Logout (Exit) | ü |  |  |  |  | - Logout (Exit)